Implementing Plan

Feature Breakdown

Frontend layer modules:

- Status and Error Display Module

- User Input Module

- Rendering Module

- Request Sending Module

Backend layer modules:

- Application Controller

- Authentication Module

- Information Acquisition Module

- Parser Module

- Data Processing Module

- Data Access Module

- Error Handling Module

Development Order

The development progress was divided into two parts: UI framework (Stage.A4) and data acquisition (Stage.A5).

Part I: UI Framework

The UI Framework section does not cover anything related to data acquisition and parsing. It simply aims to create a concise and easily readable UI framework. Therefore, this section mainly covers the development of these modules.

| Frontend layer modules | Backend layer modules |
| --- | --- |
| - Status and Error Display Module - User Input Module - Rendering Module - Request Sending Module | - Application Controller - Data Access Module - Error Handling Module |

More specifically, the development of these modules also follows a certain sequence and has its own level of complexity. Therefore, a more detailed plan is as follows:

- Day 1: Develop Rendering Module

  - Do not set trigger events for interactive elements yet.

  - Build a basic, usable UI and a framework for displaying information. The focus should be on having no obvious bugs and clear logic.

- Day 2: User Input Module.

  - Begin setting up trigger events for each interactive element.

  - Connect some of these trigger events to the Request Sending Module (which is currently just an empty function).

- Day 3: Data Access Module(No Encryption).

  - Create a local JSON file containing academic information and user settings.

  - Define the format and manually fill in test data.

  - Develop a data access module and test its ability to successfully extract data from a local JavaScript file. Encryption is not involved at this stage.

- Day 4: Application Controller + Request Sending Module

  - Develop the backend application controller and connect it to the existing backend modules.

  - Develop the frontend Request Sending Module and connect it to the existing frontend modules.

  - Establish the connection between these two modules.

- Day 5: Status and Error Display Module + Error Handing Module

  - Develop the backend-level Error Handling Module and connect it to the Application Controller.

  - Develop the frontend-level Status and Error Display Module.

  - Establish the connection between the Application Controller and the Display Module.

- Day 6: Encryption

  - Add simple encryption technology to the Data Access Module

- Day 7: Test Day.

  - Test existing structures and skeletons. Specific testing methods are detailed in the test plan section below.

Part II: Data Acquisition

Data acquisition section involves all aspects of retrieving information from TigerNet, including acquiring data, processing and cleaning data, and integrating and sending information. These modules are involved in this section:

Backend layer modules

- Authentication Module - Information Acquisition Module - Parser Module - Data Processing Module

Because the four modules form a clear data processing pipeline, the development sequence is clearly visible:

- Day 1: Authentication Module:

  - Develop the Authentication module, focusing on the login part of TigerNet.

- Day 2-3: Information Acquisition Module

  - Developing Selenium scripts to automatically retrieve raw data from TigerNet was the most tedious part of the entire system development.

  - Connecting with the Authentication Module and testing the sequential execution of the two modules were also performed.

- Day 4: Parser Module

  - Develope the parser module, focusing on cleaning the raw data obtained from the Information Acquisition Module into preliminarily usable information.

  - Test the linkage effect with the preceding production line.

- Day 5: Data Processing Module

  - Develop the data processing module to transform initially usable data into structured data that is easier for the front-end to display.

  - Test its integration with the preceding processing pipeline.

- Day 6: Module Connection

  - Connect the existing data processing pipeline to the Application Controller: the Application Controller sends information to the Authentication Module, and then the Data Processing Module returns the finished product information.

  - Establish connections between the Application Controller for academic information and between the Data Access Module and the Rendering Module.

- Day 7: Test Day

  - Test the existing data acquisition and processing pipeline, as well as the triggering from front-end interactions. See the test plan section below for specific testing methods.

File/Module Structure

The project will be organized based on the system architecture decomposition. The frontend files will focus on user interaction, visual display, and sending requests to the backend. The backend files will focus on controlling the workflow, handling login, retrieving information, parsing data, processing data, storing data, and handling errors:

SL_project

- main.py

- Frontend/

- App_Window.py

- Input_Module.py

- Request_Module.py

- Status_Error_Display.py

- Backend/

- Application_Controller.py

- Authentication.py

- Data_Acquisition.py

- Parser.py

- Processer.py

- Error_Handler.py

- Storage/

- Academic_info.js

- User_setting.js

Risk List

The main risks of this project are related to web automation, data accuracy, privacy, and project scope.

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Tigernet webpage structure changed | The Selenium script failed to recognize the original tags, causing information retrieval to fail. | The modules in the data processing pipeline are decoupled from each other. This allows for faster identification of the problematic module and prevents the repair from affecting other modules. |
| Poor network or no connection during data acquisition | The web page took too long to load, causing a timeout and data retrieval failure. | Store the last successful data locally so the app can still display old information |
| Incorrect login information | Retrieval fails | Show clear error messages instead of crashing |
| Sensitive account information is mishandled | Privacy or security concern | Keep data local and avoid unnecessary storage of passwords |
| Scope becomes too large | MVP may not be completed on time | Prioritize the core requirements: retrieve, refresh, store, organize, and display information |

Testing Strategy Outline

The primary purpose of this part is to ensure the usability and stability of the MVP product. Testing mainly consists of three parts: individual module testing, integration testing and user simulation scenario testing.

First, each module will be tested. For example, the parser should be tested using sample HTML data, and the local storage module should be tested to ensure that data can be saved and loaded correctly.

Second, integration testing will check whether the main workflow works effectively across the modules. For example, clicking the refresh button should send a request to the backend, retrieve or process the data, save it locally, and update the frontend display.

Third, user scenario testing will check common real-world use cases, including successful login, failed login, no network connection, slow TigerNet loading, offline display, and refreshing when old data already exists.

The MVP will be considered successful if the application can open and display simulated or stored data, retrieve at least one type of real academic information by manually refreshing, save it locally, and display easy-to-understand error messages when problems occur.